## Creative Agency Test Case
Test Summary Report
Project Name | Creative Agency
Total Test Cases | 47
Pass | 26
Failed | 20
Not Executed | 1
Out Of Scope | 0
SL | Test Case Id | Module | Features | Type Of Testing | Test Cases | Test Data | Expected Result | Actual Result | Reproducing Steps | Bug Screen Shot | Status | Dev Comments | Severity | Improvement Scope (any)
1 | test_01 | Home | Navbar | UI | Check the home content visibility | N/A | user can view the full home page content | Not As Expected ( broken texts on tab) | 1. Go to Chrome Browser. 2.Go to creative agency site 3. Observe the home page content | https://prnt.sc/8teu2_5sv4VD | Failed
2 | test_02 |  |  | UI | Check tha navbar align items | N/A | Align items should be properly show on every devices | Not As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3.Go to Navbar 4. oberserver the navbar | https://prnt.sc/C4LFKSI6EtbM | Failed
3 | test_03 |  | Banner | UI | Check the banner content show properly on every devices | N/A | Banner content must show properly on all devices | Not As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3.Go to Banner Section 4. oberserver the Banner content | https://prnt.sc/CKxzvTKa641- | Failed
4 | test_04 |  |  | functional | Check the hire button clickability | N/A | hire button must be clickable and it will go to desired page | Not As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3.Go to Banner Section 4. Click the hire button | https://prnt.sc/UfweChowVq-G | Failed
5 | test_05 |  | Logout | functional | Check the Logout button clickability | N/A | button should be workable and it will logout the user | As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3.Go to Banner Section 4. Click the Logout button |  | Passed
6 | test_06 |  | Our Partners | UI | Check the Our partners content visibility | N/A | content must be visible in all devices | As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3.Go to Our Partner Section 4. Observe the our partner content |  | Passed
7 | test_07 |  | Awesome Sevices | UI | Check the services visibility to all the devices | N/A | Services must be visible to all devices | Not As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3.Go to Our Partner Section 4. Observe the our partner content | https://prnt.sc/2E808-eKHC2D | Failed
8 | test_08 |  | Place Order | functional | Check the Place Order button clickability | N/A | button must be clickable and it will go to different page | As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3.Go to Our Awesome Service Section 4. Observe our Awesome Service content |  | Passed
9 | test_09 |  |  | functional | Name & email field must be fixed based on users login | N/A | User can not edit or change email | Not As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3.Click The Place Order Page 4. Go to Place order page 5. | https://www.loom.com/share/d5b7d70f4c1e41008e3a7de2e440fce4 | Failed
10 | test_10 |  |  | functional | Address & city can not contain only number | N/A | Address & city must be string not only numbers | Not As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3.Click The Place Order Page 4. Go to Place order page 5. Enter city & address as number | https://prnt.sc/PkmgPnx__3R2 | Failed
11 | test_11 |  |  | functional | Phone Number must be valid & 11 digits number | N/A | Phone number must be 11 digits & valid phone Number | Not As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3.Click The Place Order Page 4. Go to Place order page 5. Enter invalid phone number & enter less than 11 digits number | https://prnt.sc/zgI2j52fJDbq | Failed
12 | test_12 |  |  | functional | Date must be valid Date format | mm/dd/yyyy | Date must be valid format |  | 1. Go to Chrome Browser. 2.Go to creative agency site 3.Click The Place Order Page 4. Go to Place order page 5. Enter valid date format
13 | test_13 |  |  | UI | Check the Place Order Page visibility on all devices | N/A | Place Order page must be visible to all devices | As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3.Go to Our Awesome Service Section 4. Click the purchase button 5. visualize the place order page |  | Passed
14 | test_14 |  |  | UI | Check the sevices alignment to all devices | N/A | Services must be on correct alignment | Not As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3.Go to Our Awesome Service Section 4. Observe the awsome service content | https://prnt.sc/Vald-wlLx2_a | Failed
15 | test_15 |  | Some of Our Works | Ui | Check the some of our works visibility | N/A | Content must be visible in all devices | As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3.Go to Our Some Of Works Section 4. Observe the Some Of Works Section |  | Passed
16 | test_16 |  |  | functional | Check the some of our works slider workability | N/A | Slider must be workable in all devices | As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3.Go to Our Some Of Works Section 4. Observe the Some Of Works Section Slider |  | Passed
17 | test_17 |  | Customer Reviews | UI | Check the customer reviews visibility | N/A | It must be visible to all devices | Not As Expected ( broken on small device) | 1. Go to Chrome Browser. 2.Go to creative agency site 3.Go to Our Some Of Works Section 4. Observe the Some Of Works Section Slider | https://prnt.sc/hPCL7VWEwXfm | Failed
18 | test_18 |  | Contact | UI | Check the contact header texts margin | N/A | it must have perfect margin | Not As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3.Go to Contact Section 4. Observe the Contact Section | https://prnt.sc/JZSk6s-YP5hq | Failed
19 | test_19 |  |  | functional | Verify the submit form with valid data in contact form | name: pabon, designation: Junior software Engineer, description: here I have working for 1 year | it must submit the form & success alert will be showed | Not As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3.Go to Cotact Section 4. Fill up the form with valid data 5. submit the form | https://www.loom.com/share/e75af541eae44500b4d1a18413bd7577 | Failed
20 | test_20 |  |  | functional | Check the empty contact form submission | data: empty | it must not submit the form & error message will be showed | As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3.Go to Contact Section 4. Fill up the form with valid data 5. submit the form |  | Passed
21 | test_21 |  |  | functional | Verify the submit form with invalid data | name: @!AB designation: 123 description: 45678 | it must not submit the form & error message will be showed | Not As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3.Go to Footer Section 4. Fill up the form with invalid data 5. submit the form | https://www.loom.com/share/003e65712f174a3baec6231238e0fb83 | Failed
22 | test_22 | Explore | Products | Ui | Check the explore products visibility in all devices | N/A | itt must be visible in all devices | Not As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3.Go to Explore Page. 4. Observe the Product section | https://prnt.sc/qC2K5A7qbGJc | Failed
23 | test_23 |  |  | Ui | Check the explore products alignment in all devices | N/A | it must be proper alignment in all devices | Not As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3.Go to Explore Page. 4. Observe the Product section | https://prnt.sc/H9wuVdvHIqNF | Failed
24 | test_24 |  |  | Ui | Check the products image visibility in all devices | N/A | image must be show on every devices | Not As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3.Go to Explore Page. 4. Observe the Product Image | https://prnt.sc/GWAaEnH49-25 | Failed
25 | test_25 | Portfolio |  | functional | Check the portfollio menu link clickability | N/A | portfolio link must be clickable it will go to different page | Not As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3. Click On Portfolio link 4. Observe the output | https://www.loom.com/share/6500c7f51a944b9ea6891aa546112d3b | Failed
26 | test_26 | User Dashboard |  | functional | Check the all user dashboard menu items clickability | N/A | menu items must be clickable | As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3. Login as User 4. Go to User Dashboard 5. Click the dashboard menu items |  | Passed
27 | test_27 |  |  | Ui | Check the User dashboard content visibility | N/A | items must be visible | Not As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3. Login as User 4. Go to User Dashboard 5. Observe the dashboard content | https://prnt.sc/92rFxOquenIK | Failed
28 | test_28 |  | Payment | Ui | Check the payment content visibility | N/A | content must be visible in every devices | As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3. Login as User 4. Go to User Dashboard 5. Observe the dashboard content |  | Passed
29 | test_29 |  | Review | functional | Verify the review form submission with valid data | img: https://images.pexels.com/photos/2379004/pexels-photo-2379004.jpeg?auto=compress&cs=tinysrgb&dpr=1&w=500 , name: jack , comment: Good , rating: 5 | form must be submitted success message will show | As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3. Login as User 4. Go to User Dashboard 5.go to review section 6. Enter the form with valid data 7. Submit the form |  | Passed
30 | test_30 |  |  | functional | Verify the review form submission with empty data | data: empty | form must not be submitted & error message will be show | Not As Expected (No error message showing) | 1. Go to Chrome Browser. 2.Go to creative agency site 3. Login as User 4. Go to User Dashboard 5.go to review section 6. Enter the form with valid data 7. Submit the form | https://www.loom.com/share/7098f07144d7496b94968c17a3ac7897 | Failed
31 | test_31 |  |  | functional | Verify the review form submission with invalid rating and invalid name | name: ABC, rating: -5 | form must not be submitted & error message will be show | Not As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3. Login as User 4. Go to User Dashboard 5.go to review section 6. Enter the form with valid data 7. Submit the form | https://prnt.sc/p1ByciOrtfNO | Failed
32 | test_32 |  |  | functional | Verify the review form submission with empty img field & invalid name & description | img: ""; name: 12343255246 | form must not be submitted & error message will be showed | Not as Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3. Login as User 4. Go to User Dashboard 5.go to review section 6. Enter the form with valid data 7. Submit the form | https://prnt.sc/SMYE4H7BTRiv | Failed
33 | test_33 |  |  | functional | Description field must not be more than 50 words | this is goodthis is goodthis is goodthis is good ......... | Description must not be more than 50 words | Not As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3. Login as User 4. Go to User Dashboard 5.Go to review section 6. Enter the form with valid data 7. Submit the form | https://prnt.sc/3ImvDiD5Lr3y | Failed
34 | test_34 |  | My Orders | Ui | Check the visibility of my orders page in all devices | N/A | orders page should be visible on all devices | As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3. Login as User 4. Go to User Dashboard 5. Go to my orders page. |  | Passed
35 | test_35 |  |  | functional | Verify the cancel order button clickability | N/A | A confirm alert message will come & Order will be canceled sucessfully | As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3. Login as User 4. Go to User Dashboard 5. Go to my orders page. 6. Click the cancel order & observe. |  | Passed
36 | test_36 | Admin Dashboard | Add new Service | functional | Check the add new service form with valid data | name: SQA, description: Software quality assurance (SQA) ......., price: 50$, img: https://www.comstarusa.com/storage/2020/09/software-quality-assurance.png | A new service will be added | As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3. Login as Admin 4. Go to Admin Dashboard 5.Go to Add new Service. 6. Click the cancel order & observFill up the form with valid data & submit |  | Passed
37 | test_37 |  |  | functional | Check the add new service form with valid data with duplicate submission | name: SQA, description: Software quality assurance (SQA) ......., price: 40$, img: https://www.comstarusa.com/storage/2020/09/software-quality-assurance.png | only a new service will be added not duplication added | As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3. Login as Admin 4. Go to Admin Dashboard 5.Go to Add new Service. 6. Click the cancel order & observe 7. Fill up the form with valid data & submit |  | Passed
38 | test_38 |  | Manage Orders | UI | Check the manage Orders page visibility | N/A | manager orders page should be visible to all pages | As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3. Login as Admin 4. Go to Admin Dashboard 5.Go to manage Orders Page. 6. Ob serve the page |  | Passed
39 | test_39 |  |  | functional | Verify the approve button clickability | N/A | approve button should be clickable | As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3. Login as Admin 4. Go to Admin Dashboard 5.Go to manage Orders Page. 6. Click the Approve button |  | Passed
40 | test_40 |  |  | functional | Verify the approve button clickability after the status has been shipped | N/A | approve button must be disable after status has been shipped | Not As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3. Login as Admin 4. Go to Admin Dashboard 5.Go to manage Orders Page. 6. Click the Approve button .7 Again click the approve button when status is shipped | https://prnt.sc/w2BlI-VZ_sqp | Failed
41 | test_41 |  |  | functional | Verify the delete button clickability of manage orders | N/A | delete button must be clickable and order will be deleted | As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3. Login as Admin 4. Go to Admin Dashboard 5.Go to manage Orders Page. 6. Click the delete button 7. Observe the delete button |  | Passed
42 | test_42 |  | Manage Products | Ui | check the manage products page visibility | N/A | It muist be visible to all devices | As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3. Login as Admin 4. Go to Admin Dashboard 5.Go to manage Products Page. |  | Passed
43 | test_43 |  |  | Ui | check the text alignment of manage products | N/A | it must be correct alignmnt ( content should be in left and right part) in all devices | Not As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3. Login as Admin 4. Go to Admin Dashboard 5.Go to manage Products Page. 6. Observe the text content | https://prnt.sc/gn9VniPU0d7y | Failed
44 | test_44 |  |  | Ui | check the image visibility of products in all devices | N/A | image must be visible on every devices | Not As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3. Login as Admin 4. Go to Admin Dashboard 5.Go to manage Products Page. 6. Observe the text content | https://prnt.sc/qeL7T_cdeiJR | Failed
45 | test_45 |  |  | functional | Check the delete button clickability in Products page | N/A | delete button must be clickable and order will be deleted | Not As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3. Login as Admin 4. Go to Admin Dashboard 5.Go to manage Products Page. 6. delete the product | https://www.loom.com/share/34b46f2ea407429d929849944841b304 | Failed
46 | test_46 |  | Add admin | UI | Check the add new admin visibility | N/A | It muist be visible to all devices | As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3. Login as Admin 4. Go to Admin Dashboard 5.Go to make admin page 6. visualize the admin page |  | Passed
47 | test_47 |  |  | functional | Check the add new admin form clickability | email: hasin@gmail.com | user must be able as admin | Not As expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3. Login as Admin 4. Go to Admin Dashboard 5.Make one user admin . 6. Then Logout 7. Again Login with that new role admin user. 8. Go to dashboard. 9. Observe the dashboard | https://prnt.sc/XxhmgikFBYXT | Failed
48 | test_48 | Our Team |  | Ui | Verify our Team page visibility in all devices | N/A | Our team page must be visible in all devices | As Expected | 1. Go to Chrome Browser. 2.Go to creative agency site 3. go to Our team page. 4. Observe the our team page |  | Passed
49 | test_49 | Registration |  | functional | Verify the Registration page with valid username, email & password & empty image field | image: "", username: hasin12, email: hasin12@gmail.com, password: 123456 | User can not register & error message will be showed | Not As Expected | 1. Go to Chrome Browser. 2.Go to registration page. 3. fill up the form without image field 4. Submit the form | https://www.loom.com/share/c9840c393b5348d2a67bf284f6498379 | Failed
50 | test_50 |  |  | functional | Verify the registration page with empty field form submission | data: empty | User can not register | As Expected | 1. Go to Chrome Browser. 2.Go to registration page. 3. fill up the form without image field 4. Submit the form |  | Passed
51 | test_51 |  |  | functional | Verify the registration page with invalid email,name | name: 123, email: 123, password: 123456 | User can not register | Not as expected | 1. Go to Chrome Browser. 2.Go to registration page. 3. fill up the form with invalid name & email 4. Submit the form | https://www.loom.com/share/9c7c514e410741f4a8bd9d7ce7e42782 | Failed
52 | test_52 |  |  | functional | Verify the registration page with weak password | name: hasin14, email: hasin14@gmail.com, password; 111111 | user can not register | Not as expected | 1. Go to Chrome Browser. 2.Go to registration page. 3. fill up the form with invalid name & email 4. Submit the form | https://www.loom.com/share/f3ace74e44164266944a957836404a0e | Failed
53 | test_53 | Login |  | functional | verify the login page with empty form submission | data: empty | user can not login | As Expected | 1. Go to Chrome Browser. 2.Go to login page. 3. fill up the form with iempty data. 4. submit the form |  | Passed
54 | test_54 |  |  | functional | verify the login page with invalid email & password | email; hasin20@gmail.com, pass: 111111 | user can not login | As Expected | 1. Go to Chrome Browser. 2.Go to login page. 3. fill up the form with invalid email & password. 4. submit the form |  | Passed
55 | test_55 |  |  | functional | verify the login page with empty email & valid password | email; "", password: 111111 | user can not login | As Expected | 1. Go to Chrome Browser. 2.Go to login page. 3. fill up the form with invalid email & password. 4. submit the form |  | Passed
56 | test_56 |  |  | functional | verify the login page with valid email & empty password | email; hasin14@gmail.com, pass:"" | user can not login | As Expected | 1. Go to Chrome Browser. 2.Go to login page. 3. fill up the form with valid email and empty password. 4. submit the form |  | Passed
57 | test_57 |  |  | functional | verify the login page with valid email & password | email; hasin14@gmail.com, pass:111111 | user can login | As Expected | 1. Go to Chrome Browser. 2.Go to login page. 3. fill up the form with valid email and empty password. 4. submit the form |  | Passed

## MindMap
MINDMAP

## Creative Agency Test Metrics
BDShop TEST METRICS
Sl | Metrics | Result %
1 | Test Case Executed | 97.87 %
2 | Test Case Not Executed | 2.12%
3 | Test Case Passed | 56.52%
4 | Test Case Failed | 43.48%
5 | Test Case Blocked | 0%
6 | Deffect Density | 0
7 | Deffect Leakage | 0
8 | Customer Statisfaction | 0
9 | Deffect Removal Efficiency | 0

## Test Case Report
Test Case Report
Project Name | Creative Agency
Module Name | Home, Explore, Portfolio, User Dashboard, Admin Dashboard, Our Team, Registration, Login
Written By | Hasin Anjum Pabon
Executed By | Hasin Anjum Pabon
Reviewed By | Hasin Anjum Pabon
Test Execution Report
Test Case | Pass | Failed | Not Executed | Out Of Scope | Total Test Cases
| 26 | 20 | 1 | 0 | 47
Grand Total | 26 | 20 | 1 | 0 | 47

## Bug Report
SL | Bug Id | Bug Description | Module | Environment | Reproducing Steps | Source Url | Attachments | Severity | Priority | Responsible QA
1 | bug_01 | taking invalid name on name field | Registration | Chrome | 1. Go to Chrome Browser. 2.Go to registration page. 3. fill up the form with invalid name 4. Submit the form | https://creative-agency-552c2.web.app/registration | https://www.loom.com/share/9c7c514e410741f4a8bd9d7ce7e42782 | High | High | Hasin Anjum Pabon
2 | bug_02 | taking registration page with weak password | Registration | Chrome | 1. Go to Chrome Browser. 2.Go to registration page. 3. fill up the form with invalid name 4. Submit the form | https://creative-agency-552c2.web.app/registration | https://www.loom.com/share/f3ace74e44164266944a957836404a0e | High | High | Hasin Anjum Pabon